## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Subodh Kamble
Document Created On: | 20/04/2024
Version: | 4
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Project Schedule
PROJECT Schedule/Plan
DOCUMENT VERSION: 4.0
PROJECT NAME | CodeCruise CI/CD Pipeline solution |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED ON THE RIGHT HAND SIDE TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | DevOps CI/CD pipeline Solution
PROJECT SCOPE
PROJECT START DATE | 2024-02-15
PROJECT END DATE | 2024-05-10
OVERALL PROGRESS | Completed
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify business problem |  | 20/2/2024 | 20/2/2024 | 1 | COMPLETED
| 1.3 Create a project charter |  | 20/2/2024 | 20/2/2024 |  | COMPLETED
| 1.4 Requirement gathering |  | 20/2/2024 | 2024-01-03 | 9 | COMPLETED
2 Planning
| 2.1 System design and Architecture design |  | 2024-01-03 | 15/3/2024 | 5 | COMPLETED
| 2.2 Baseline project plan |  | 2024-01-03 | 15/3/2024 | 10 | COMPLETED
3 Execution
| 3.1 Finalize design |  | 15/03/2024 | 20/04/2024 | 35 | COMPLETED
| 3.2 Build |  |  |  |  | COMPLETED
| 3.2.1 Features |  |  |  |  | COMPLETED
| GCP CLoud Instance setup and configurations |  |  |  |  | COMPLETED
| jenkins server setup and configurations |  |  |  |  | COMPLETED
| Docker Script and Application simple Development for test |  |  |  |  | COMPLETED
| Pipeline 1 (github sonarqube OWASP check) |  |  |  |  | COMPLETED
| Pipeline 2 (Trivy reports , Email notifications) |  |  |  |  | COMPLETED
| 3.3 Testing |  | 20/4/2024 | 2024-02-05 | 14 | COMPLETED
| 3.3.1 Manual testing (self build using jenkins) |  |  |  |  | COMPLETED
| 3.3.2 Automation testing (Github webhook Trigger) |  |  |  |  | COMPLETED
| 4 Closure |  | 2024-10-05 | 2024-10-05 | 1 | COMPLETED